February 10th, 2026

Monica Winemiller

General Motors

Warren, Michigan

Dear Monica,

Thank you for the opportunity to collaborate with General Motors through the University of Michigan’s Engineering Consulting Group. Our goal is to develop a strategic plan that streamlines manual processes, shows supplier SG&A and profit data over time, and sets cost standards efficiently. This Letter of Execution serves to confirm our mutual understanding of the project’s objectives, scope, approach, timing, deliverables, and resource requirements. We look forward to working closely with you and your team throughout the semester.

Project Motivation and Objective

The primary objective of MECG’s engagement with General Motors is to develop a streamlined dashboard and conduct analysis that enables the PPCO team to effectively assess supplier financial performance over time. Our team will gather publicly available data and calculate SG&A and profit metrics to support cost standards for supplier negotiations.

The goal of this project is to help the PPCO team reduce manual processes, save time, and improve the efficiency of cost decision-making. The accessible tool will allow users to conveniently view and analyze General Motors supplier SG&A and profit trends across multiple years. The dashboard will enable the team to create more efficient cost decision-making and negotiation metrics.

Project Scope

To accomplish the project objective, MECG will:

- Gather publicly available financial data, such as revenue, SG&A, and EBIT, for key suppliers

- Develop an overall standard used as a target during negotiations

- Identify trends and insights across suppliers to inform cost standards and supplier evaluation

- Streamline manual processes to reduce time spent on data collection and analysis

- Develop a dashboard that presents financial data for specific suppliers over a period of time

Project Constraints

Important considerations that shape the project include:

- Ensuring a smooth transition at the conclusion of project engagement

- Solutions must be scalable and stay within General Motors’s internal resource constraints.

- Focus on suppliers relevant to General Motors’s current products.

- The dashboard and process should be designed to be sustainable, easy to use, and accessible after MECG’s involvement concludes.

- All financial data and analyses rely on publicly available sources; some suppliers are owned by private equity firms making income statements inaccessible

Approach and Timing

The engagement is expected to span approximately 8-10 weeks. Our time and effort will be structured as follows:

Phase A: Research & Discovery (2 weeks)

- Understand how supplier financial data is sourced, calculated, and used

- Identify current pain points and inefficiencies within PPCO’s supplier financial analysis

- Assess existing tools, dashboards, and manual-based processes

- Collect available financial data on publicly traded companies

- Identify key suppliers and those that are public vs. private

Phase B: Financial Analysis & Standards Development (2 weeks)

- Analyze and clean publicly available supplier financial data as well as trends and variability

- Calculate key financial metrics, such as SG&A and profit percentages, to determine an overall standard used as a target in supplier negotiating

- Find a platform that best fits the scope of the project including, but not limited to, integration capabilities, security, technical needs and user constraints

Phase C: Dashboard Development & Process Streamlining (3 weeks)

- Build a prototype tool to visualize supplier financial metrics

- Conduct pilot testing with PPCO employees and refine the tool accordingly

- Evaluate the dashboard’s effectiveness in reducing manual effort and improving accessibility

- Collect feedback from PPCO to refine usability

Phase D: Strategic Recommendations and Implementation (2 weeks)

- Create documentation and clear instructions for using, updating, and maintaining the dashboard

- Deliver a final dashboard that presents supplier financial metrics over time

- Present findings and recommendations for future process improvements

- Propose strategies for ensuring sustainability after MECG’s involvement

Deliverables

MECG will provide you with midpoint and final deliverables, written reports, and slide decks that summarize findings and recommendations. We will update you with our research, progress, and strategy throughout the project. We are very excited to be working with General Motors, and we look forward to delivering a meaningful tool that will have a lasting impact on your company!

Sincerely,

Daniel Okoye, MECG Project Manager

Luciano Del Carpio, Giada Garzelloni, Nandini Tatiwala, Jihyo Yoo